## E2E QA Report
TC_ID | Module | Test_Case | Endpoint_or_Page | Expected_Result | Actual_Result | Status | Severity | Owner | Retest_Status | Executed_On | Notes
E2E-01 | Authentication | Admin login | POST /api/auth/login | 200 and token returned | Login success with token | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Auth works
E2E-02 | Customer | Create customer | POST /api/customers | Customer created with ID | Created customer_id=2 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Create flow works
E2E-03 | Customer | View customer | GET /api/customers/{id} | 200 with created customer details | Fetched customer_id=2 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Read flow
E2E-04 | Customer | Update customer | PUT /api/customers/{id} | 200 and updated fields persisted | Updated phone=9000000002 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Update flow
E2E-05 | Vehicle | Create vehicle | POST /api/vehicles | Vehicle created with ID and number | Created vehicle_id=3, number=QA20260402120332 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Create flow works
E2E-06 | Vehicle | View vehicle by number | GET /api/vehicles/{vehicle_number} | 200 with matching vehicle | Fetched number=QA20260402120332 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Read flow
E2E-07 | Vehicle | Update vehicle | PUT /api/vehicles/{vehicle_number} | 200 and updated fields persisted | Updated type=Luxury Bus, seats=35 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Update flow
E2E-08 | Driver | Create driver | POST /api/drivers | Driver created with ID | Created driver_id=2 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Create flow works
E2E-09 | Driver | View driver | GET /api/drivers/{id} | 200 with created driver | Fetched driver_id=2 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Read flow
E2E-10 | Vendor | Create vendor | POST /api/vendors | Vendor created with ID | Created vendor_id=2 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Create flow works
E2E-11 | Vendor | List vendors includes new record | GET /api/vendors | Created vendor should appear in list | Vendor present in list | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Read/list flow
E2E-12 | Vendor | Vendor summary load | GET /api/vendors/{id}/summary | Summary endpoint should respond 200 | Summary fetched | Pass | Low | Backend/Frontend | Pending | 2026-04-02 | Summary endpoint check
E2E-13 | Quotation | Create quotation | POST /api/quotations | Quotation created with ID | Created quotation_id=2 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Create flow works
E2E-14 | Quotation | View quotation | GET /api/quotations/{id} | 200 with quotation details | Fetched quotation_id=2 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Read flow
E2E-15 | Quotation | Update quotation | PUT /api/quotations/{id} | 200 and updated values persisted | Updated customer_name=QA Customer 20260402120332 Updated | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Update flow
E2E-16 | Trip | Create trip with invoice number | POST /api/trips | Trip created with ID and invoice no | Created trip_id=1, invoice=INV-20260402120332 | Pass | High | Backend/Frontend | Pending | 2026-04-02 | Core business flow
E2E-17 | Trip | View trip details | GET /api/trips/{id} | 200 with created trip details | Fetched trip_id=1, invoice=INV-20260402120332 | Pass | High | Backend/Frontend | Pending | 2026-04-02 | Trip read flow
E2E-18 | Customer/Trip | Customer trips includes created trip | GET /api/customers/{id}/trips | Created trip should be linked under customer | Trip linked under customer | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Relational consistency
E2E-19 | Payment | Create payment for trip | POST /api/payments | Payment created and linked to trip | Created payment_id=1, invoice=INV-20260402120332 | Pass | High | Backend/Frontend | Pending | 2026-04-02 | Payment flow works
E2E-20 | Payment | Trip payment history | GET /api/payments/trip/{trip_id} | Payment list should include created payment | Payments found count=1 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Payment retrieval
E2E-21 | Invoice | Invoice source data (trip) | GET /api/trips/{trip_id} | Trip endpoint should provide invoice_number and charge data | invoice_number=INV-20260402120332 | Pass | High | Backend/Frontend | Pending | 2026-04-02 | Invoice backend dependency
E2E-22 | Invoice UI | Invoice page route load | GET /invoices/{trip_id} | Invoice route should load SPA HTML | Status=200 | Pass | Medium | Backend/Frontend | Pending | 2026-04-02 | Frontend route availability
E2E-23 | Cleanup | Delete test payment | DELETE /api/payments/{id} | Payment should delete successfully | Deleted payment | Pass | Low | Backend/Frontend | Pending | 2026-04-02 | Cleanup
E2E-24 | Cleanup | Delete test trip | DELETE /api/trips/{id} | Trip should delete successfully | Deleted trip | Pass | Low | Backend/Frontend | Pending | 2026-04-02 | Cleanup
E2E-25 | Cleanup | Delete test quotation | DELETE /api/quotations/{id} | Quotation should soft-delete successfully | Deleted quotation | Pass | Low | Backend/Frontend | Pending | 2026-04-02 | Cleanup
E2E-26 | Cleanup | Delete test vendor | DELETE /api/vendors/{id} | Vendor should delete successfully | Deleted vendor | Pass | Low | Backend/Frontend | Pending | 2026-04-02 | Cleanup
E2E-27 | Cleanup | Delete test vehicle | DELETE /api/vehicles/{id} | Vehicle should delete successfully | Deleted vehicle | Pass | Low | Backend/Frontend | Pending | 2026-04-02 | Cleanup
E2E-28 | Cleanup | Delete test customer | DELETE /api/customers/{id} | Customer should delete successfully after trip cleanup | Deleted customer | Pass | Low | Backend/Frontend | Pending | 2026-04-02 | Cleanup
E2E-29 | Cleanup | Deactivate test driver | DELETE /api/drivers/{id} | Driver deactivation should succeed | Driver deactivated | Pass | Low | Backend/Frontend | Pending | 2026-04-02 | Cleanup

## Summary
Metric | Value
Total Test Cases | 29
Passed | 29
Failed | 0
Executed On | 2026-04-02